## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Define Problem Statement, Objectives, and Modular Architecture for AI-Powered Customer Support Quality Auditor (AIPCSQA) | MUST HAVE | Brief + workflow | Dhruti Mahadik | 3- Completed
S1 | S1 | US-002 | Set up FastAPI backend, PostgreSQL configuration, and core SQLAlchemy models for users, calls, transcripts, audits, violations, and reports | MUST HAVE | FastAPI + PostgreSQL | Dhruti Mahadik | 3- Completed
S2 | S2 | US-003 | Implement JWT authentication and role-based access for supervisor and agent portals | MUST HAVE | JWT + auth router | Dhruti Mahadik | 3- Completed
S3 | S3 | US-004 | Build call upload flow, transcript storage, and AssemblyAI speaker diarization pipeline | MUST HAVE | AssemblyAI + uploads | Dhruti Mahadik | 3- Completed
S4 | S4 | US-005 | Create Flipkart policy knowledge base and TF-IDF RAG retrieval service for grounded responses | MUST HAVE | Policies + TF-IDF | Dhruti Mahadik | 3- Completed
S5 | S5 | US-006 | Develop AI customer simulation with 10 Flipkart scenarios, gTTS voice output, and mixed-audio recording | SHOULD HAVE | Groq + gTTS + Web Audio | Dhruti Mahadik | 3- Completed
S6 | S6 | US-007 | Implement AI audit scoring across empathy, compliance, resolution, professionalism, and communication with silent-agent protection | MUST HAVE | Groq audit + scoring | Dhruti Mahadik | 3- Completed
S7 | S7 | US-008 | Build supervisor and agent dashboards with KPIs, leaderboard, transcript review, and live monitor | MUST HAVE | React UI + live monitor | Dhruti Mahadik | 3- Completed
S8 | S8 | US-009 | Generate PDF reports, finalize deployment configuration, and complete end-to-end testing and documentation | SHOULD HAVE | reports.py + Render | Dhruti Mahadik | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 78 | 22 | 12 | 11 | 9 | 10 | 13 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Finalize problem statement, objectives, and sprint plan | 2026-02-02 | 2026-02-04 | Yashwanth Krishna | Design | 3- Completed | 5 | 1 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Set up FastAPI project structure and environment configuration | 2026-02-05 | 2026-02-06 | Tanbir | Build | 3- Completed | 6 | 3 | 1 | 0 | 0 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Create SQLAlchemy models for User, Agent, Call, Transcript, Audit, Violation, and Report | 2026-02-09 | 2026-02-11 | Ojaswini | Coding | 3- Completed | 8 | 1 | 0 | 0 | 2 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Implement JWT auth, password hashing, and role-based protected routes | 2026-02-13 | 2026-02-16 | Vansh | Coding | 3- Completed | 5 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 5 | Build audio upload flow and AssemblyAI speaker diarization integration | 2026-02-17 | 2026-02-19 | Dhruri Mahadik | Integration Test | 3- Completed | 6 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Prepare Flipkart policy chunks and TF-IDF RAG retrieval service | 2026-02-20 | Coding | 3- Completed | Coding | 3- Completed | 10 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Develop AI customer simulation scenarios with gTTS mixed-audio flow | 2026-02-25 | Build | 3- Completed | Build | 3- Completed | 4 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | Implement AI audit engine, grading rubric, and silent-agent protection | 2026-03-02 | Coding | 3- Completed | Coding | 3- Completed | 5 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 8 | Add compliance violation detection and dashboard aggregation APIs | 2026-03-06 | Integration Test | 3- Completed | Unit Test | 3- Completed | 10 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 9 | Build React agent and supervisor portal views with KPI cards and leaderboard | 2026-03-13 | Build | 3- Completed | Build | 3- Completed | 6 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 10 | Generate PDF reports and real-time live monitor updates | 2026-03-18 | Build | 3- Completed | Integration Test | 3- Completed | 8 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 11 | Deployment, end-to-end testing, and README documentation hardening | 2026-03-25 | System Test | 2- In Progress | System Test | 3- Completed | 5 | 2 | 1 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Scope overlap between supervisor and agent portal responsibilities | Created an owner matrix and split backlog items by module
Sprint 2 | Day 7 | Async PostgreSQL connection issues during local backend setup | Standardized .env configuration and validated database bootstrap
Sprint 3 | Day 10 | JWT role checks were failing for protected routes | Refactored token dependency and added route-level auth tests
Sprint 4 | Day 13 | Speaker diarization mislabeled agent and customer in longer recordings | Tested sample audio and added transcript cleanup checks
Sprint 5 | Day 16 | RAG retrieval returned irrelevant policy chunks for some queries | Refined query cleanup, chunking, and top-k retrieval logic
Sprint 6 | Day 21 | Groq audit output varied across scoring dimensions | Tightened prompt rubric and added fallback scoring safeguards
Sprint 7 | Day 25 | Dashboard updates lagged during live monitor events | Optimized WebSocket broadcast flow and reduced refresh overhead
Sprint 8 | Day 27 | PDF report layout overflowed for long summaries | Trimmed verbose content and adjusted report formatting

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-05-02 | Vansh | Validate scope before coding | Assuming task ownership is obvious | Sprint planning and mentor syncs | Added owner matrix and backlog review checklist
2 | Sprint 3 | 2026-12-02 | 19/2/2026 | Ojaswini | Review API contracts before implementation | Testing routes only at the end of the sprint | Modular router-based development | Prepared smoke tests before each merge
3 | Sprint 4 | 23/2/2026 | 27/2/2026 | Tanbir | Check transcript samples daily | Assuming diarization output is always clean | Iterative debugging with sample calls | Added transcript QA before running audit scoring
4 | Sprint 6 | 2026-02-03 | 2026-06-03 | Yashwanth Krishna | Run dashboard performance checks earlier | Keeping too much logic inside one UI file | Rapid demo feedback cycles | Reduced UI bottlenecks and simplified refresh logic
5 | Sprint 8 | 2026-10-03 | 16/3/2026 | Dhruti Mahadik | Use a release checklist before demo day | Last-minute environment changes | Documentation updates and knowledge sharing | Updated documentation and shared project knowledge with team for better understanding.